## TBS Implementation update point
TBS IMPLEMENTATION OVERVIEW POINTS
S/N | Items | Receive Date | Status | Comments
1 | Dynamic content report on tbs | 2021-01-27 | Pending
2 | Profile: Call center remark not displaying after been saved. | 2021-01-27 | Verified | Done
3 | Customer code is blank | 2021-01-27 | Verified | Done
4 | IATA insurance on BTMAdventures is blank despite been save on the profile. | 2021-01-27 | Verified | Done
5 | Hotel not populated on Amadeus | 2021-01-27 | Pending | Done
6 | Hotel currency values should be in USD and not NGN, also hotel result from amadeus is showing 1 star | 2021-01-27 | Pending | Amadues return based on country
7 | Tour Package not been populated on btmadventures | 2021-01-27 | Pending | Done
8 | Tour image gallery | 2021-01-27 | Verified | Done
9 | Offline PNR: Update dates from the past on segment 1 | 2021-01-27 | Verified | Done
10 | Travel Quotation: Ability to queue | 2021-01-27 | Pending
11 | Destiination Advice: Nationality should not default to Brazil but Nigeria. Suggestion: keep travel details blank | 2021-01-27 | Verified | Done
12 | Spelling correction on Passenger Profile not profilee | 2021-01-27 | Verified | Done
13 | Access to hotel inventory for TBS. Hotel loaded on marketplace should display also on tbs hotel | 2021-01-27 | Pending | Done
14 | Hotel history tab for local inventory | 2021-01-27 | Pending | Done
15 | Hotel Inventory Edit option |  |  | Not Done

## Marketplace Implementn updt
Markeplace Overview
S/N | Items | Received date | Status | Comment
1 | No company info to display | 2021-01-27 | Verified | Done
2 | Marketplace should not have access to booking page | 2021-01-27 | Verified | Done
4 | Sign in agents should only see their populated records and not all records. | 2021-06-28 | Verified | Done
5 | Under Manager Service, remove all option leaving only Add Tour Package as the option for other agents users. But for 'HO' users all options must be available. | 2021-06-28 | Verified | Done
6 | Under Details Report page Unauthorized Access message is displayed. Please rectify, so that each login agent can generate their respective reports. | 2021-06-28 | Verified | Done
7 | Add a checkbox in package upload to specified if package is a featured package. | 2021-07-23 | Verified | Done
9 | Maintain uploaded image size and quality. | 2021-07-23 | Verified | Done
10 | Error message while trying to upload package using an external agency ID. agency id: 5764 | 2021-10-05 | Verified | Done
11 | Error uploading Hotel package using external user login ID. | 2021-10-06 | Verified | Done
12 | Package cannot be modify. Alert: No Package Available | 2021-10-06 | Verified | Done

## BTM Adventures updt
S/N | Items | Received date | Status | Comment | Feedback / Response
1 | Package deals to display both tour and hotel packages | 2021-01-27 | Verified | Done
2 | Reporting on btm adventures (Google Analytics) | 2021-01-27 | Pending
3 | Most recent package to be display on btm adventures homepages under "Travel adventures are back again" | 2021-01-27 | Verified | Done
4 | Change all protocol text to conceige. | 2021-01-27 | Verified | Done
5 | Take out supplier icons on btm adventures bookings | 2021-01-27 | Verified | Done
6 | Error while making hotel search on btmadventures | 2021-01-27 | Verified | Done
7 | Supplier on btmadventures hotel result to be removed | 2021-01-27 | Verified | Done
8 | Hotel star rating to be checked from proper star rating. | 2021-01-27 | Pending
9 | Hotel facilities to have the tooltip text on hover | 2021-01-27 | Verified | Done
10 | Hotel content to also display local inventory | 2021-01-27 | Pending | Done
11 | BTM browser tab name to be modify to BTMAdventures | 2021-01-27 | Verified | Done
12 | Logo to be bigger | 2021-01-27 | Verified | Done
13 | Packages to Hotel Package |  | Verified | Done
14 | Package Image Not shown |  | Verified | Done
15 | Text and Font sizes too small across the site | 2021-02-15 | Verified | Done
16 | Mobile Optimization | 2021-04-15 | Verified | Done
17 | No display on searched hotels | 2021-05-19 | Pending | Supplier Side Issue
18 | Incorrect search hotel price | 2021-05-19 | Pending
19 | Remove semicolon (:) on cancellation policy. Both on alertbox and hotel details page. | 2021-05-19 | Pending
20 | Hotel detail page: Slider thumbnails to display images. See cell B95 | 2021-05-19 | Verified | Done
21 | Billing Information: Fields should be blank. | 2021-05-19 | Verified | Done
22 | Hotel Details: Booking summary: Remove strikethrough USD value | 2021-05-19 | Verified | Done
23 | Hotel Details: Accurate charges to be displayed. | 2021-05-19 | Pending | Done
24 | Homepage: Create hyperlinks to each section on 'we handle Everything from'. Hyperlink to redirect to each booking element. | 2021-05-19 | Pending | Done
25 | Concierge service section: This section should be replace with other services (car hire, meet&greet, concierge etc). With easy to make bookings | 2021-05-19 | Pending | Done
26 | Menu: About link should properly match the about section on the homepage. | 2021-05-19 | Verified | Done
27 | Signup form: Remove default Lagos value on city. | 2021-05-19 | Verified | Done
28 | Signup form: Submit button text to be replace with Join BTM Adventures | 2021-05-19 | Verified | Done
29 | Currency coversion on tour package and holiday package details page. | 2021-05-19 | Pending | Done
30 | Tour package booking form: Add date input for user to select available date for package. (Date selection should be within range of the package dates). | 2021-05-19 | Verified | Done
31 | Package price to be seperated using a semi-colon. (e.g 120,000) | 2021-05-19 | Verified | Done
32 | Tour package and holiday package booking form: Added input to auto calculate package value. ie if either adult or child button is click, the total price should be updated. See cell b51 | 2021-05-19 | Verified | Done
33 | Homepage: Holiday package open date should be shown/checked by default. | 2021-05-19 | Verified | Done
34 | Image: Enusre all displayed images are not streched. | 2021-05-19 | Verified | Done
35 | Blog: Ensure blog images are rendered properly with definite dimensions | 2021-05-19 | Verified | Need more clarification | Highlighted point is from our end. Image dimension is 250X400 (pixels)
36 | Package click-bait design | 2021-05-19 | Pending | Need more clarification
37 | chatbot for adventures | 2021-05-19 | Pending
38 | This is the display of the downloaded package. | 2021-09-17 | Verified | Image result shared via Whatsapp | Done
39 | Can we just upload the package PDF file when package is been created? This can easily be downloaded when the button is clicked on. | 2021-09-17 | Verified |  | Done
40 | Homepage: The blog section in the home page should display 4 recent uploads and a button to redirect to the blog page where all post will be displayed. | 2021-09-17 | Verified |  | Done
41 | Kindly look into the cause of some images not been displayed | 2021-09-17 | Verified | Image result shared via Whatsapp | Done
42 | Blogpage: The url to view the post is not working. Kindly check. | 2021-09-17 | Verified | Image result shared via Whatsapp | Done
43 | Email id field type should be email and not number, currently accepting numbers. | 373192 | Verified | Image result shared via Whatsapp | Done
44 | email address obstructing paystack. | 373192 | Verified | Image result shared via Whatsapp | Done
45 | Reduce logo size for menu list to fit in horizontally. | 373192 | Pending | Image result shared via Whatsapp | Done
46 | No alert after form is submitted. Page remain static | 373192 | Verified | Image result shared via Whatsapp | Done

## TBF
S/N | Items | Received date | Status
1 | .ipa iOs beta application expected | 2021-02-15 | Received
2 | .apk Android beta application expected | 2021-02-15 | Received
3 | Landing page: 'Go back' link should be remove | 2021-05-02 | Verified | Done
4 | Sliders should contain relevants images | 2021-05-02 | Verified | Done
5 | Sign up page: Facebook and Gmail link button not functioning | 2021-05-02 | Pending
6 | Sign up page: 'Sign in' link not redirecting to sign on page | 2021-05-02 | Verified | Done
7 | Password reset failed | 2021-05-02 | Pending | Done
8 | After login, the back button redirect user to login page. It should be remove. | 2021-05-02 | Pending | This is still redirecting to the login page after login has been made
9 | Trek' menu option stops the application and exit | 2021-05-02 | Pending | Done
10 | Buy' landing page should have an header. | 2021-05-02 | Pending | No Header yet
11 | Hotel results not displaying images | 2021-05-02 | Pending | No Image result yet
12 | Hotel results showing 1 star for all hotels | 2021-05-02 | Pending | Horel Response 1 star for Amadeus Hotel
13 | Slider thumbnials on hotel details should be remove. | 2021-05-02 | Verified | Done
14 | Back button not functioning on selected hotel page. | 2021-05-02 | Verified | Done
15 | Flight result filter not working | 2021-05-02 | Pending | Done
16 | No booking option button for selected package | 2021-05-02 | Pending | Done
17 | Setting, notification, help and support menu options not responding | 2021-05-02 | Pending
18 | On profile page, menu button not responding. | 2021-05-02 | Pending | Done
19 | Trip, coupon, badge options not working on profile page. | 2021-05-02 | Pending | please send the details
20 | Change password on profile page truncate the application. | 2021-05-02 | Pending | Done

## Journeyeasy
Journeyeasy Implementation overview
S/N | Items | Receive Date | Status | Comments | Feedback / Comments
1 | Email notification should be sent from journeyeasy@gmail.com | 2021-01-22 | Pending | The SMTP server requires a secure connection or the client was not authenticated. The server response was: 5.7.0 Authentication Required. Learn more at
2 | Agent manual form fill to replicate on journeyeasy registration | 2021-01-22 | Verified | DONE | Form has been updated to required need.
3 | All form filled to be capture on email notifiation to be sent to hello@journeyeasy | 2021-01-22 | Verified | DONE
4 | Sign In/up should be change to Sign In | 2021-01-22 | Verified | DONE
5 | Point value on hover to be change to 'Available point value' | 2021-01-22 | Verified | DONE
6 | Successful Alert message to consist of the following "Thank you for joining the JourneyEasy Family. Registration successful" | 2021-01-22 | Verified | DONE
7 | Journeyeasy Dashboard: Make point and Credit balance appear side by side | 2021-01-22 | Verified | DONE
8 | PDF for Journeyeasy sub agent manual should be made available on the dashboard | 2021-01-22 | Verified | DONE
9 | Paystack: Remove credit limit and leave current balance | 2021-01-22 | Verified | DONE
11 | Flight: Flight search to default to Personal | 2021-01-22 | Verified | DONE
12 | GDS checkbok on flight search to be removed. | 2021-01-22 | Verified | DONE
13 | Flight search result: Number of seat indicator should show 'Seat Available' | 2021-01-22 | Verified | DONE
14 | No supplier filters for fights and GDS filters | 2021-01-22 | Verified | DONE
15 | Captcha to be change automatically on each visit | 2021-01-22 | Verified | DONE
16 | Agent manual form fill to replicate on journeyeasy registration | 2021-01-22 | Verified | DONE
17 | RBD Disable in JE | 2020-01-22 | Verified | DONE
18 | Registration page more information |  |  | DONE
19 | No points |  |  | DONE
20 | package to Hotel Package |  |  | DONE
21 | Sub Agent form fields adjustment. | 2021-04-08 |  | DONE
22 | Is there a way an alternative username can be generated on the site (if the one selected is already in use), rather than having to email it to them? | 2021-04-08 |  | Field has been removed because the system only requires email for login and as well the used as the default username.
23 | Can we also generate a section for profile pictures or logos to be uploaded as they fill the form as against having to email their profile pictures or logos to us? | 2021-04-08 | Verified | DONE
24 | On the contact page, the font color used for the phone number and email address is a bit hard to see. | 2021-04-08 | Verified | DONE
25 | Successful Alert message to consist of the following "Thank you for joining the JourneyEasy Family. Registration successful." | 2021-04-09 |  | DONE
26 | The Company/ Preferred JourneyEasy Portal name / Company Alternative Name fields should be replaced with "What JourneyEasy brand name would you prefer to use on your profile? e.g GeeGee Travel Limited | 2021-04-09 | Verified | DONE
27 | There should be a space in the text beside the check box “I am happy to receive promotions via all the above” | 2021-04-09 | Verified | DONE
28 | Kindly update 'Company/ Prefered Journeyeasy Portal name' to 'Company/ Preferred Journeyeasy Portal name' | 2021-04-09 |  | Field has been removed.
29 | The reason for recommendation field should be removed. | 2021-04-09 | Verified | DONE
30 | Flight search result: Remove village label | 2021-05-19 | Verified | DONE
31 | Hotel tab: Remove HOTB checkbox | 2021-05-19 | Verified | DONE
32 | Hotel tab: check all star rating as default. Change square box to star icon. | 2021-05-19 | Verified | DONE
33 | Hotel content should populating results from hotelspro, hotelbed, only GDS and BTM content are been shown. | 2021-05-19 | Verified | Need more clarification
34 | Hotel searched result not fetching records | 2021-05-19 | Pending | Need more clarification
35 | Car Rental: Change checkIn to Pickup and CheckOut to Drop off | 2021-05-19 | Pending
36 | Tour Packages: Images not displayed on both search result page and details page | 2021-05-19 | Pending | DONE
37 | Add semi-colon to price value both on search result page and details page | 2021-05-19 | Pending | DONE
38 | Package booking form: Number of added passenger should auto reflect on the total price | 2021-05-19 | Pending | DONE
39 | Error on package form submit: Procedure or function 'SVC_BOOKMyTourPackage' expects parameter '@Country', which was not supplied. | 2021-05-19 | Verified | DONE
40 | Dashboard: Agent balance font to be more visible and bold | 2021-05-19 | Verified | DONE
41 | Point balance to be displayed on the dashboard. | 2021-05-19 | Pending | DONE
42 | Saleswise error: Unable to process your request. | 2021-05-19 | Verified | DONE
43 | Error Alert on package details page. See cell B54 | 2021-05-19 | Verified | DONE
44 | Hotel package image not showing. | 2021-06-02 | Pending | DONE
45 | Package details page not showing package value. See cell 76 | 2021-06-02 | Verified | If Hotel Package Register Please Enter The Amount In Room Selection. | DONE
46 | Before page load, the dashboard is slightly displayed for seconds. Can we disable that effect. | 2021-06-02 | Pending |  | Once complete I will update